## Projects
Project_ID | Client_Name | Project_Type | Address | Start_Date | End_Date | Estimated_Cost | Actual_Cost | Status | Crew_Lead
P1001 | Brown Residence | New Build | 5870 Pine Street | 2025-08-01 | 2025-10-27 | 261424 | 287476 | Delayed | Rick
P1002 | Martinez Homes | Deck/Patio | 3203 Elm Street | 2025-08-26 | 2025-10-21 | 20341 | 23259 | Completed | Rick
P1003 | Brown Residence | Renovation | 3726 Oak Street | 2025-08-13 | 2025-11-16 | 123267 | 108997 | Completed | Devon
P1004 | Johnson Residence | Deck/Patio | 2553 Elm Street | 2025-08-12 | 2025-09-30 | 16255 | 16286 | Delayed | Tasha
P1005 | Chen Builders | Roofing | 748 Oak Street | 2026-02-08 | 2026-04-10 | 27691 | 24741 | Delayed | Maria
P1006 | Johnson Residence | Roofing | 2207 Elm Street | 2025-09-08 | 2025-09-24 | 28720 | 27882 | Completed | Devon
P1007 | Davis Family | Roofing | 1517 Oak Street | 2025-01-12 | 2025-02-03 | 37055 | 41942 | Completed | Jake
P1008 | Davis Family | Deck/Patio | 8257 Oak Street | 2025-10-09 | 2025-10-19 | 9190 | 8428 | Completed | Rick
P1009 | Jackson Residence | Renovation | 1654 Cedar Street | 2025-06-23 | 2025-09-22 | 115056 | 121570 | Completed | Tasha
P1010 | Wilson Properties | Addition | 6758 Elm Street | 2026-02-16 | 2026-04-23 | 65874 | 73431 | Completed | Rick
P1011 | Johnson Residence | Roofing | 9475 Maple Street | 2026-02-07 | 2026-04-16 | 33791 | 31227 | Completed | Maria
P1012 | Moore Renovations | Roofing | 6758 Cedar Street | 2026-02-20 | 2026-04-13 | 31546 | 35959 | Completed | Maria
P1013 | Taylor Family | Deck/Patio | 997 Elm Street | 2026-02-10 | 2026-05-02 | 23043 | 26494 | Completed | Tasha
P1014 | Garcia Home | Roofing | 8809 Maple Street | 2025-09-12 | 2026-01-05 | 24068 | 23834 | Delayed | Rick
P1015 | Davis Family | Roofing | 6529 Pine Street | 2026-02-18 | 2026-05-16 | 19511 | 19078 | Delayed | Rick
P1016 | Garcia Home | New Build | 7662 Elm Street | 2025-03-10 | 2025-03-25 | 347374 | 356419 | Completed | Maria
P1017 | Wilson Properties | Renovation | 2160 Cedar Street | 2025-10-05 | 2025-11-02 | 140571 | 159460 | Completed | Devon
P1018 | Garcia Home | Addition | 5653 Pine Street | 2025-11-23 | 2026-01-17 | 71828 | 65545 | Completed | Maria
P1019 | Garcia Home | Addition | 3793 Oak Street | 2025-11-06 | 2025-12-19 | 113505 | 123387 | Completed | Rick
P1020 | Jackson Residence | Roofing | 2432 Elm Street | 2026-02-22 | 2026-03-17 | 37808 | 33004 | In Progress | Jake
P1021 | Smith Family | Renovation | 5771 Pine Street | 2025-09-14 | 2025-11-10 | 88362 | 95308 | Completed | Maria
P1022 | Wilson Properties | Deck/Patio | 3485 Maple Street | 2026-01-22 | 2026-03-25 | 13605 | 14748 | Completed | Maria
P1023 | Davis Family | Addition | 7279 Oak Street | 2025-12-08 | 2026-02-27 | 108078 | 113896 | Completed | Tasha
P1024 | Johnson Residence | Deck/Patio | 189 Pine Street | 2025-09-03 | 2025-12-08 | 9694 | 9280 | Completed | Maria
P1025 | Taylor Family | Addition | 9837 Elm Street | 2025-09-15 | 2025-10-28 | 87301 | 80787 | In Progress | Jake
P1026 | Jackson Residence | Roofing | 7811 Pine Street | 2026-01-13 | 2026-03-07 | 16393 | 15353 | In Progress | Jake
P1027 | Williams Estate | Deck/Patio | 8436 Oak Street | 2025-12-25 | 2026-03-09 | 27690 | 27398 | Completed | Jake
P1028 | Smith Family | Roofing | 3951 Cedar Street | 2025-12-03 | 2026-03-15 | 25054 | 21609 | Completed | Tasha
P1029 | Taylor Family | Renovation | 5451 Elm Street | 2025-10-05 | 2025-11-09 | 84451 | 78746 | Delayed | Tasha
P1030 | Smith Family | Addition | 6606 Elm Street | 2025-07-02 | 2025-07-17 | 146183 | 143798 | Completed | Devon

## Materials
Purchase_ID | Project_ID | Material_Type | Supplier | Quantity | Unit_Price | Total_Cost | Purchase_Date
MAT10001 | P1001 | Hardware | Quality Builders | 73 | 38.8694 | 2837.4684 | 2025-09-10
MAT10002 | P1001 | Lumber | Elite Construction Supply | 100 | 4.7574 | 475.7424 | 2025-10-16
MAT10003 | P1002 | Drywall | BuildRight Supplies | 45 | 24.995 | 1124.7771 | 2025-10-10
MAT10004 | P1002 | Paint | Quality Builders | 38 | 44.5787 | 1693.9911 | 2025-09-11
MAT10005 | P1003 | Roofing | Elite Construction Supply | 7 | 3.57 | 24.9901 | 2025-11-13
MAT10006 | P1003 | Plumbing | Elite Construction Supply | 21 | 16.3362 | 343.0593 | 2025-09-07
MAT10007 | P1003 | Lumber | Quality Builders | 70 | 7.4244 | 519.7112 | 2025-10-26
MAT10008 | P1004 | Electrical | Quality Builders | 59 | 18.3898 | 1084.9957 | 2025-09-09
MAT10009 | P1004 | Lumber | Quality Builders | 68 | 3.984 | 270.9128 | 2025-09-20
MAT10010 | P1004 | Paint | Quality Builders | 20 | 44.487 | 889.7398 | 2025-09-26
MAT10011 | P1005 | Paint | Elite Construction Supply | 99 | 54.195 | 5365.3044 | 2026-02-12
MAT10012 | P1005 | Electrical | Elite Construction Supply | 93 | 31.4275 | 2922.756 | 2026-03-01
MAT10013 | P1005 | Drywall | Quality Builders | 33 | 12.2902 | 405.5752 | 2026-04-04
MAT10014 | P1006 | Lumber | Pro Materials Co | 17 | 8.9973 | 152.9544 | 2025-09-17
MAT10015 | P1006 | Drywall | Quality Builders | 49 | 12.8098 | 627.682 | 2025-09-17
MAT10016 | P1007 | Roofing | Quality Builders | 55 | 5.0519 | 277.8538 | 2025-01-24
MAT10017 | P1008 | Plumbing | Elite Construction Supply | 77 | 188.3433 | 14502.4369 | 2025-10-09
MAT10018 | P1009 | Roofing | Elite Construction Supply | 23 | 5.5473 | 127.5876 | 2025-07-01
MAT10019 | P1010 | Electrical | Quality Builders | 52 | 32.6607 | 1698.3561 | 2026-03-26
MAT10020 | P1011 | Paint | Elite Construction Supply | 31 | 42.8587 | 1328.6184 | 2026-02-20
MAT10021 | P1011 | Drywall | Quality Builders | 15 | 17.6855 | 265.2823 | 2026-04-12
MAT10022 | P1011 | Plumbing | Elite Construction Supply | 31 | 70.0334 | 2171.036 | 2026-04-02
MAT10023 | P1012 | Hardware | BuildRight Supplies | 43 | 59.5054 | 2558.7301 | 2026-03-18
MAT10024 | P1012 | Lumber | Elite Construction Supply | 82 | 2.3815 | 195.2793 | 2026-04-13
MAT10025 | P1013 | Roofing | Quality Builders | 79 | 6.1841 | 488.5426 | 2026-04-05
MAT10026 | P1014 | Electrical | Pro Materials Co | 7 | 38.9786 | 272.8505 | 2025-12-06
MAT10027 | P1015 | Hardware | BuildRight Supplies | 39 | 24.0042 | 936.165 | 2026-05-11
MAT10028 | P1016 | Lumber | Pro Materials Co | 60 | 2.7816 | 166.899 | 2025-03-23
MAT10029 | P1016 | Paint | Quality Builders | 85 | 32.5229 | 2764.4507 | 2025-03-18
MAT10030 | P1016 | Hardware | Quality Builders | 24 | 8.2237 | 197.3688 | 2025-03-21
MAT10031 | P1017 | Drywall | BuildRight Supplies | 18 | 14.3261 | 257.8705 | 2025-10-25
MAT10032 | P1018 | Drywall | Pro Materials Co | 12 | 20.0485 | 240.582 | 2025-12-18
MAT10033 | P1018 | Paint | Quality Builders | 89 | 31.7442 | 2825.2312 | 2025-12-11
MAT10034 | P1019 | Plumbing | Elite Construction Supply | 14 | 71.612 | 1002.5685 | 2025-12-14
MAT10035 | P1020 | Concrete | BuildRight Supplies | 75 | 145.665 | 10924.8721 | 2026-03-10
MAT10036 | P1020 | Roofing | Quality Builders | 48 | 4.2594 | 204.4526 | 2026-03-06
MAT10037 | P1021 | Drywall | Pro Materials Co | 39 | 17.6886 | 689.8543 | 2025-10-30
MAT10038 | P1022 | Electrical | BuildRight Supplies | 98 | 23.1554 | 2269.2251 | 2026-02-25
MAT10039 | P1023 | Drywall | Quality Builders | 22 | 15.0936 | 332.0592 | 2026-01-24
MAT10040 | P1023 | Electrical | Elite Construction Supply | 43 | 6.0195 | 258.8368 | 2026-02-15
MAT10041 | P1023 | Roofing | BuildRight Supplies | 79 | 3.9851 | 314.8248 | 2026-02-27
MAT10042 | P1024 | Concrete | Elite Construction Supply | 52 | 144.4341 | 7510.571 | 2025-10-12
MAT10043 | P1025 | Drywall | BuildRight Supplies | 8 | 14.5659 | 116.5273 | 2025-10-07
MAT10044 | P1025 | Paint | Pro Materials Co | 78 | 39.5455 | 3084.5466 | 2025-10-14
MAT10045 | P1026 | Hardware | Elite Construction Supply | 37 | 55.749 | 2062.7131 | 2026-02-12
MAT10046 | P1027 | Drywall | Pro Materials Co | 57 | 23.4904 | 1338.9539 | 2026-03-07
MAT10047 | P1027 | Paint | Pro Materials Co | 75 | 42.2797 | 3170.981 | 2026-01-16
MAT10048 | P1028 | Paint | Elite Construction Supply | 37 | 43.6084 | 1613.509 | 2026-02-15
MAT10049 | P1028 | Concrete | BuildRight Supplies | 40 | 149.0535 | 5962.1403 | 2026-02-23
MAT10050 | P1029 | Plumbing | BuildRight Supplies | 72 | 148.3443 | 10680.7904 | 2025-11-04
MAT10051 | P1029 | Roofing | Elite Construction Supply | 35 | 6.6512 | 232.7913 | 2025-10-27
MAT10052 | P1029 | Lumber | Elite Construction Supply | 38 | 3.3388 | 126.8746 | 2025-10-14
MAT10053 | P1030 | Paint | Pro Materials Co | 78 | 55.824 | 4354.2757 | 2025-07-05
MAT10054 | P1030 | Plumbing | Pro Materials Co | 66 | 123.1866 | 8130.316 | 2025-07-07
MAT10055 | P1030 | Roofing | BuildRight Supplies | 24 | 7.0801 | 169.9226 | 2025-07-13

## Labor
Entry_ID | Project_ID | Worker_Name | Role | Hours_Worked | Hourly_Rate | Week_Ending | Total_Pay
LAB10001 | P1001 | Mike | Carpenter | 26 | 32.6976 | 2025-09-12 | 850.1372
LAB10002 | P1001 | Rachel | Electrician | 16 | 35.2404 | 2025-09-12 | 563.8461
LAB10003 | P1001 | Daniel | Carpenter | 17 | 36.4482 | 2025-09-26 | 619.6193
LAB10004 | P1002 | Karen | Plumber | 26 | 35.4789 | 2025-10-10 | 922.4522
LAB10005 | P1002 | James | Laborer | 49 | 24.9759 | 2025-09-12 | 1223.8201
LAB10006 | P1003 | David | Carpenter | 43 | 32.5268 | 2025-11-07 | 1398.6539
LAB10007 | P1003 | Robert | Foreman | 41 | 42.0776 | 2025-11-14 | 1725.18
LAB10008 | P1003 | Jennifer | Electrician | 9 | 39.7131 | 2025-11-07 | 357.4177
LAB10009 | P1003 | James | Laborer | 35 | 20.6608 | 2025-11-14 | 723.1263
LAB10010 | P1004 | Amanda | Carpenter | 14 | 34.8739 | 2025-09-19 | 488.2343
LAB10011 | P1004 | Karen | Plumber | 37 | 35.0662 | 2025-09-12 | 1297.4481
LAB10012 | P1004 | Carlos | Foreman | 34 | 40.9147 | 2025-09-26 | 1391.0983
LAB10013 | P1005 | David | Plumber | 19 | 34.2751 | 2026-03-20 | 651.2276
LAB10014 | P1005 | Tom | Plumber | 36 | 39.4684 | 2026-04-03 | 1420.8629
LAB10015 | P1005 | Jennifer | Electrician | 45 | 41.5308 | 2026-04-03 | 1868.8842
LAB10016 | P1005 | Sarah | Foreman | 38 | 44.8021 | 2026-04-03 | 1702.48
LAB10017 | P1006 | Rachel | Electrician | 15 | 35.2538 | 2025-09-12 | 528.8076
LAB10018 | P1006 | Carlos | Laborer | 28 | 21.8176 | 2025-09-19 | 610.8933
LAB10019 | P1006 | Amanda | Carpenter | 22 | 34.5515 | 2025-09-19 | 760.1333
LAB10020 | P1007 | Lisa | Electrician | 35 | 39.1308 | 2025-01-24 | 1369.5778
LAB10021 | P1007 | James | Foreman | 27 | 40.8549 | 2025-01-17 | 1103.0828
LAB10022 | P1007 | Amanda | Plumber | 24 | 32.0295 | 2025-01-10 | 768.7074
LAB10023 | P1008 | David | Plumber | 48 | 34.5232 | 2025-10-17 | 1657.116
LAB10024 | P1008 | Mike | Carpenter | 32 | 35.4934 | 2025-10-10 | 1135.789
LAB10025 | P1008 | Daniel | Electrician | 26 | 36.4469 | 2025-10-10 | 947.6202
LAB10026 | P1008 | Sarah | Plumber | 48 | 37.6513 | 2025-10-10 | 1807.2626
LAB10027 | P1009 | Karen | Foreman | 25 | 42.9286 | 2025-08-01 | 1073.2157
LAB10028 | P1009 | Michelle | Laborer | 31 | 19.6137 | 2025-08-08 | 608.0241
LAB10029 | P1009 | James | Foreman | 37 | 44.4348 | 2025-09-19 | 1644.0889
LAB10030 | P1010 | Lisa | Foreman | 9 | 41.7362 | 2026-04-17 | 375.6257
LAB10031 | P1010 | Lisa | Plumber | 32 | 33.0831 | 2026-04-17 | 1058.6598
LAB10032 | P1010 | Lisa | Foreman | 36 | 44.232 | 2026-04-24 | 1592.3514
LAB10033 | P1011 | Antonio | Laborer | 21 | 22.0117 | 2026-03-20 | 462.2461
LAB10034 | P1011 | David | Laborer | 12 | 20.0214 | 2026-04-17 | 240.2569
LAB10035 | P1012 | Mike | Electrician | 30 | 40.1677 | 2026-03-13 | 1205.03
LAB10036 | P1012 | Antonio | Laborer | 24 | 18.6125 | 2026-02-27 | 446.6995
LAB10037 | P1013 | Carlos | Carpenter | 12 | 30.5211 | 2026-02-13 | 366.2528
LAB10038 | P1013 | Robert | Plumber | 46 | 33.1697 | 2026-03-06 | 1525.8046
LAB10039 | P1014 | Amanda | Foreman | 50 | 40.3024 | 2025-12-19 | 2015.1224
LAB10040 | P1014 | Mike | Laborer | 35 | 24.1534 | 2025-10-24 | 845.3677
LAB10041 | P1015 | Amanda | Plumber | 28 | 41.1949 | 2026-04-03 | 1153.4568
LAB10042 | P1015 | Sarah | Carpenter | 49 | 36.1746 | 2026-02-20 | 1772.5571
LAB10043 | P1015 | Rachel | Foreman | 15 | 41.4015 | 2026-03-20 | 621.022
LAB10044 | P1015 | David | Foreman | 43 | 44.1572 | 2026-05-08 | 1898.7613
LAB10045 | P1016 | David | Carpenter | 22 | 29.711 | 2025-03-14 | 653.6416
LAB10046 | P1016 | Lisa | Foreman | 46 | 43.6218 | 2025-03-21 | 2006.6017
LAB10047 | P1016 | Rachel | Foreman | 19 | 42.8596 | 2025-03-21 | 814.3332
LAB10048 | P1016 | Antonio | Laborer | 48 | 21.2493 | 2025-03-21 | 1019.9675
LAB10049 | P1017 | Carlos | Plumber | 19 | 33.4198 | 2025-10-31 | 634.9753
LAB10050 | P1017 | Rachel | Electrician | 50 | 40.0972 | 2025-10-31 | 2004.8622
LAB10051 | P1017 | Robert | Laborer | 22 | 18.723 | 2025-10-31 | 411.9067
LAB10052 | P1018 | Michelle | Carpenter | 40 | 35.1268 | 2026-01-16 | 1405.071
LAB10053 | P1018 | Carlos | Electrician | 15 | 42.2525 | 2025-12-26 | 633.787
LAB10054 | P1018 | Amanda | Electrician | 30 | 36.3406 | 2025-11-28 | 1090.2187
LAB10055 | P1019 | Antonio | Carpenter | 24 | 32.7889 | 2025-12-05 | 786.9343
LAB10056 | P1019 | Carlos | Foreman | 49 | 41.6867 | 2025-11-14 | 2042.6491
LAB10057 | P1019 | Daniel | Foreman | 49 | 42.3715 | 2025-12-12 | 2076.2021
LAB10058 | P1020 | Lisa | Foreman | 13 | 40.2081 | 2026-02-27 | 522.7049
LAB10059 | P1020 | Antonio | Foreman | 8 | 40.2291 | 2026-02-27 | 321.8331
LAB10060 | P1021 | Sarah | Plumber | 14 | 33.9348 | 2025-09-26 | 475.0871
LAB10061 | P1021 | James | Laborer | 25 | 23.1499 | 2025-11-07 | 578.7486
LAB10062 | P1022 | Sarah | Laborer | 20 | 21.5084 | 2026-01-30 | 430.1672
LAB10063 | P1022 | Karen | Electrician | 32 | 37.6353 | 2026-03-13 | 1204.3299
LAB10064 | P1022 | Sarah | Plumber | 37 | 40.1766 | 2026-02-13 | 1486.5327
LAB10065 | P1023 | Rachel | Electrician | 44 | 39.693 | 2026-01-23 | 1746.492
LAB10066 | P1023 | Jennifer | Laborer | 13 | 21.7734 | 2026-02-13 | 283.0548
LAB10067 | P1023 | Tom | Laborer | 19 | 20.9055 | 2025-12-12 | 397.2036
LAB10068 | P1024 | Lisa | Foreman | 26 | 43.2957 | 2025-10-17 | 1125.6886
LAB10069 | P1024 | Carlos | Plumber | 26 | 40.6156 | 2025-10-17 | 1056.0062
LAB10070 | P1025 | Jennifer | Foreman | 18 | 42.1647 | 2025-09-26 | 758.9649
LAB10071 | P1025 | Jennifer | Foreman | 10 | 39.864 | 2025-09-26 | 398.6401
LAB10072 | P1025 | Rachel | Laborer | 16 | 19.3916 | 2025-10-10 | 310.2648
LAB10073 | P1025 | Rachel | Plumber | 19 | 40.4886 | 2025-10-24 | 769.2841
LAB10074 | P1026 | David | Plumber | 37 | 37.169 | 2026-01-23 | 1375.2528
LAB10075 | P1026 | Antonio | Plumber | 35 | 39.9384 | 2026-02-06 | 1397.8431
LAB10076 | P1026 | Tom | Laborer | 16 | 20.2226 | 2026-03-06 | 323.5615
LAB10077 | P1026 | Jennifer | Foreman | 44 | 42.2676 | 2026-02-20 | 1859.7726
LAB10078 | P1027 | Karen | Electrician | 9 | 44.4285 | 2026-01-09 | 399.8561
LAB10079 | P1027 | Mike | Foreman | 25 | 38.3263 | 2026-03-06 | 958.1572
LAB10080 | P1028 | Lisa | Carpenter | 46 | 29.4233 | 2026-01-23 | 1353.4717
LAB10081 | P1028 | Lisa | Electrician | 13 | 41.2195 | 2026-01-16 | 535.8537
LAB10082 | P1029 | Tom | Carpenter | 14 | 29.2205 | 2025-10-17 | 409.0871
LAB10083 | P1029 | Amanda | Carpenter | 25 | 31.0894 | 2025-10-31 | 777.2347
LAB10084 | P1029 | Amanda | Plumber | 37 | 41.93 | 2025-10-31 | 1551.4086
LAB10085 | P1030 | James | Carpenter | 47 | 36.6754 | 2025-07-18 | 1723.7418
LAB10086 | P1030 | Robert | Plumber | 9 | 41.7651 | 2025-07-04 | 375.8858